## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
3 | As a customer, I want to pay for a book, So that I can own it | Product Owner | Critical | 5 | Completed | DoD1 | Testing required
16 | As a seller, I want to add a book to the system, so that I can sell it to customers | Product Owner | Critical | 3 | Completed | DoD1 | Testing required
4 | As an admin, I want to approve new user accounts so that I can grant them more features | Product Owner | Critical | 2 | Completed | DoD1
19 | As a customer, I want to buy mutliple books at the same time, so that I can make a single purchase | Product Owner | Critical | 2 | Completed | DoD1
21 | As a user, I want to sign up, So that my information is stored | Product Owner | Critical | 2 | Completed | DoD1
22 | As a registered user, I want to sign in, so that I can access my account | Product Owner | Critical | 2 | Completed | DoD1
7 | As a customer, I want to view the catalogue of books, So that I can see if a book is available | Product Owner | Critical | 2 | Completed | DoD1 | Testing required
10 | As a registered customer, I want to sell used books, So that I can give it to another person | Product Owner | Critical | 5 | Completed | DoD1
12 | As an admin, I want to reject new user accounts so that I can prevent them from accessing the full system | Product Owner | Critical | 2 | Completed | DoD1
1 | As a customer, I want to search for books, So that I can find certain books to buy | Product Owner | High | 5 | Completed | DoD1 | Testing required
28 | As a customer, I want to buy the same book multiple times at once, so that I can own that book | Product Owner | High | 5 | Completed | DoD1
2 | As a customer, I want to leave a review on a book, So that I can give my thoughts | Product Owner | High | 2 | Completed | DoD1
13 | As a user, I want to be able to view the cover of a book, So that I can decide if I want to buy it | Product Owner | High | 1 | Completed | DoD1
5 | As a Customer, I want to see my list of transactions , So that I can keep track of my expenses | Product Owner | High | 5 | Completed | DoD1 | Awaiting backend but frontend skeleton works
6 | As a seller, I want to see my list of books purchased from me , So that I can keep track of my expenses | Product Owner | High | 2 | Completed | DoD1
18 | As a customer, I want to search a specific category, so that I can view related books | Product Owner | High | 3 | Completed | DoD1 | Awaiting backend for categories api and filtering
11 | As a customer, I want to view availability of a book, So that I can purchase it | Product Owner | High | 2 | Completed | DoD1 | Not in priority list. But nice to have
15 | As a user, I want to be able to edit my profile, so that I can keep my details up to date | Product Owner | Medium | 5 | Completed | DoD1
17 | As an admin, I want to be able to download a report of all sales in a period of time, So that I can analyse them | Product Owner | Medium | 3 | Completed | DoD1
8 | As an registered customer, I want to be able to cancel my order within 2 hours, So that I can undo the purchase | Product Owner | Medium | 3 | Completed | DoD1
9 | As a customer, I want to view a books description, So that I can know what the book is about | Product Owner | Medium | 1 | Completed | DoD1
23 | As a admin, I want to moderate user reviews, so that I can maintain a clean environment | Product Owner | Medium | 3 | Completed | DoD1
24 | As a customer, I want to use paypal as a payment gateway, so that I can purchase the book | Product Owner | Medium | 5 | Completed | DoD1
25 | As a admin, I want to block a user, so that I can stop them from accessing the website | Product Owner | Medium | 1 | Completed | DoD1
29 | As a customer, I want to search books based on seller, so that I can narrow down my search | Product Owner | Medium | 3 | Completed | DoD1
30 | As a customer, I want to leave a review on a seller, so that I can portray my experience | Product Owner | Medium | 5 | Completed | DoD1
31 | As a admin, I want to edit details of a book, so that It can become accurate | Product Owner | Medium | 2 | Completed | DoD1 | Testing required
26 | As a customer, I want to contact the admin, so that I can communicate | Product Owner | Low | 2 | Completed | DoD1
27 | As a customer, I want to share a book, so that I can give other people the chance to read it | Product Owner | Low | 3 | Completed | DoD1
14 | As a customer, I want to log out, so that I can leave | Product Owner | Low | 3 | Completed | DoD1
20 | As a user, I want to be able to update my password, So that I can keep my account secure | Product Owner | Low | 3 | Completed | DoD1
DoD1 -Code is written and works for standard use case. -The tests have 70% code coverage and all -unit tests are successful (green) -Unit tests code reviewed -Qualifies acceptance criteria set -The code is reviewed or was produced using the pair-programming method -100% Functional test based on AC's passed -Usability testing completed on Google Chrome (version 89) and Safari (Version 14) -Approved by the product owner -Automated Regression testing passed

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a customer, I want to view a books description, So that I can know what the book is about | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As a registered customer, I want to sell used books, So that I can give it to another person | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a customer, I want to search for books, So that I can find certain books to buy | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a customer, I want to leave a review on a book, So that I can give my thoughts | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a customer, I want to view availability of a book, So that I can purchase it | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As an admin, I want to reject new user accounts so that I can prevent them from accessing the full system | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a customer, I want to pay for a book, So that I can own it | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a user, I want to be able to view the cover of a book, So that I can decide if I want to buy it | #N/A | #N/A | #N/A | #N/A | #N/A
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | As a customer, I want to log out, so that I can leave | #N/A | #N/A | #N/A | #N/A | #N/A
12 | As an admin, I want to approve new user accounts so that I can grant them more features | #N/A | #N/A | #N/A | #N/A | #N/A
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | As a Customer, I want to see my list of transactions , So that I can keep track of my expenses | #N/A | #N/A | #N/A | #N/A | #N/A
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | As a seller, I want to see my list of books purchased from me , So that I can keep track of my expenses | #N/A | #N/A | #N/A | #N/A | #N/A
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | As a user, I want to be able to edit my profile, so that I can keep my details up to date | #N/A | #N/A | #N/A | #N/A | #N/A
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | As a customer, I want to buy mutliple books at the same time, so that I can make a single purchase | #N/A | #N/A | #N/A | #N/A | #N/A
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | As a user, I want to sign up, So that my information is stored | #N/A | #N/A | #N/A | #N/A | #N/A
23 | As a registered user, I want to sign in, so that I can access my account | #N/A | #N/A | #N/A | #N/A | #N/A
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | As an admin, I want to be able to download a report of all sales in a period of time, So that I can analyse them | #N/A | #N/A | #N/A | #N/A | #N/A