## Sprint 1
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
21 | As a user, I want to sign up, So that my information is stored | 21.1 | Create wireframe for front end | Harris |  |  | X
|  | 21.2 | Create front end for sign up page | Mazda |  |  | X
|  | 21.3 | Make front end mobile responsive | Mazda |  |  | X
|  | 21.4 | Create user database | Harris |  |  | X
|  | 21.5 | Connect database with front end to insert users | Harris |  |  | X
|  | 21.6 | Test users are inserting correctly to database | Mazda |  |  | X
12 | As an admin, I want to reject new user accounts so that I can prevent them from accessing the full system | 12.1 | Create wireframe for admin page | Danny |  |  | X
|  | 12.2 | Create front end for admin page | Danny |  |  | X
|  | 12.3 | Connect database with front end | Danny |  |  | X
|  | 12.4 | Code back end for admins to reject unapproved users | Harris |  |  | X
|  | 12.5 | Test the database entry is being updated when rejected | Clinton |  |  | X
7 | As a customer, I want to view the catalogue of books, So that I can see if a book is available | 7.1 | Create wireframe for catalogue book page | Mazda |  |  | X
|  | 7.2 | Set up code for front end structure to view | Mazda |  |  | X
|  | 7.3 | Set up with back end code to view books | Harris |  |  | X
|  | 7.4 | Test funcitonality of customer view catalogue of books | Mazda |  |  | X
4 | As an admin, I want to approve new user accounts so that I can grant them more features | 4.1 | Create wireframe for admin page | Danny |  |  | X
|  | 4.2 | Create front end for admin page | Danny |  |  | X
|  | 4.3 | Connect database with front end | Danny |  |  | X
|  | 4.4 | Code back end for admins to approve unapproved users | Harris |  |  | X
|  | 4.5 | Test the database entry is being updated when approved | Clinton |  |  | X
22 | As a registered user, I want to sign in, so that I can access my account | 22.1 | Create wireframe for front end | Clinton |  |  | X
|  | 22.2 | Create front end for login page | Mazda |  |  | X
|  | 22.3 | Make front end mobile responsive | Mazda |  |  | X
|  | 22.4 | Connect database with front end to access users | Tessa |  |  | X
|  | 22.5 | Test the system is retrieving the correct users | Clinton |  |  | X

## Sprint 2
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
3 | As a customer, I want to pay for a book, So that I can own it | 3.1 | Create wireframes | Danny |  |  | x
|  | 3.2 | Create front end for book page | Harris |  |  | x
|  | 3.3 | Create dummy payment page front end | Danny |  |  | x
|  | 3.4 | Create transaction microservice | Tessa |  |  | x
|  | 3.5 | Link transaction to transaction table | Danny |  |  | x
|  | 3.6 | Write unit tests for tasks | Clinton |  |  | x
10 | As a customer, I want to sell used books, So that I can get rid of the book | 10.1 | Create wireframe for inventory page | Harris |  |  | x
|  | 10.2 | Create front-end for selling books page | Harris |  |  | x
|  | 10.3 | Create front-end functionality for selling books | Harris |  |  | x
|  | 10.4 | Create back-end functionality for selling used books | Tessa |  |  | x
|  | 10.5 | Create unit tests | Clinton |  |  | x
11 | As a customer, I want to view availability of a book, So that I can purchase it | 11.1 | Create wireframe for book page | Harris |  |  | x
|  | 11.2 | Create front-end for viewing availability of books | Harris |  |  | x
|  | 11.3 | Create front-end functionality for viewing book availability | Harris |  |  | x
|  | 11.4 | Create back-end functionality for viewing book availability | Harris |  |  | x
|  | 11.5 | Create unit tests | Clinton |  |  | x
1 | As a customer, I want to search for books, So that I can find certain books to buy | 1.1 | Create Wireframes | Danny |  |  | x
|  | 1.2 | Create front end page design | Danny |  |  | x
|  | 1.3 | Create front end page functionality | Danny |  |  | x
|  | 1.4 | Create back end functionality | Harris |  |  | x
|  | 1.5 | Create unit tests | Clinton |  |  | x
5 | As a Customer, I want to see my list of transactions , So that I can keep track of my expenses | 5.1 | Create Wireframes | Danny |  |  | x
|  | 5.2 | Create front end page design | Danny |  |  | x
|  | 5.3 | Create front end page functionality | Danny |  |  | x
|  | 5.4 | Create back end functionality | Tessa |  |  | x
|  | 5.5 | Create unit tests | Clinton |  |  | x
9 | As a customer, I want to view a books description, So that I can know what the book is about | 9.1 | Create Wireframes | Harris |  |  | x
|  | 9.2 | Create front end page design | Harris |  |  | x
|  | 9.3 | Create front end page functionality | Harris |  |  | x
|  | 9.4 | Create back end functionality | Harris |  |  | x
|  | 9.5 | Create unit tests | Mazda |  |  | x
18 | As a customer, I want to search a specific category, so that I can view related books | 18.1 | Create Wireframes | Danny |  |  | x
|  | 18.2 | Create front end page design | Danny |  |  | x
|  | 18.3 | Create front end page functionality | Danny |  |  | x
|  | 18.4 | Create back end functionality | Harris |  |  | x
|  | 18.5 | Create unit tests | Clinton |  |  | x
16 | As a seller, I want to add a book to the system, so that I can sell it to customers | 16.1 | Create Wireframes | Danny |  |  | x
|  | 16.2 | Create front end page design | Danny |  |  | x
|  | 16.3 | Create front end page functionality | Harris |  |  | x
|  | 16.4 | Create back end functionality | Harris |  |  | x
|  | 16.5 | Create unit tests | Clinton |  |  | x
14 | As a customer, I want to log out, so that I can leave | 14.1 | Create Wireframes | Danny |  |  | x
|  | 14.2 | Create front end page design | Danny |  |  | x
|  | 14.3 | Create front end page functionality | Danny |  |  | x
|  | 14.4 | Create unit tests | Clinton |  |  | x
13 | As a user, I want to be able to view the cover of a book, So that I can decide if I want to buy it | 14.1 | Create Wireframes | Harris |  |  | x
|  | 14.2 | Create front end page design | Harris |  |  | x
|  | 14.3 | Create front end page functionality | Harris |  |  | x
|  | 14.4 | Create unit tests | Clinton |  |  | x
31 | As a admin, I want to edit details of a book, so that It can become accurate | 31.1 | Create Wireframes | Danny |  |  | x
|  | 31.2 | Create front end page design | Danny |  |  | x
|  | 31.3 | Create front end page functionality | Danny |  |  | x
|  | 31.4 | Create unit tests | Clinton |  |  | x

## Sprint 3
SPRINT #3 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
3 | As a customer, I want to pay for a book, So that I can own it | 3.1 | Create wireframes | Danny |  |  | x
|  | 3.2 | Create front end for book page | Harris |  |  | x
|  | 3.3 | Create dummy payment page front end | Danny |  |  | x
|  | 3.4 | Create transaction microservice | Tessa |  |  | x
|  | 3.5 | Link transaction to transaction table | Danny |  |  | x
|  | 3.6 | Write unit tests for tasks | Clinton |  |  | x
10 | As a registered customer, I want to sell used books, So that I can give it to another person | 10.1 | Create wireframe for inventory page | Harris |  |  | x
|  | 10.2 | Create front-end for selling books page | Harris |  |  | x
|  | 10.3 | Create front-end functionality for selling books | Harris |  |  | x
|  | 10.4 | Create back-end functionality for selling used books | Tessa |  |  | x
|  | 10.5 | Create unit tests | Clinton |  |  | x
19 | As a customer, I want to buy mutliple books at the same time, so that I can make a single purchase | 19.1 | Create shopping cart model | Harris |  |  | x
|  | 19.2 | Update front end for cart | Danny |  |  | x
|  | 19.3 | Create APIs for shopping cart | Harris |  |  | x
|  | 19.4 | Link shopping cart with transactions | Harris |  |  | x
|  | 19.5 | Create tests | Clinton |  |  | x
28 | As a customer, I want to buy the same book multiple times at once, so that I can own that book | 28.1 | Update front end to allow multiple purchases | Danny |  |  | x
|  | 28.2 | Link front end with transactions model | Harris |  |  | x
|  | 28.3 | Create tests | Clinton |  |  | x
2 | As a customer, I want to leave a review on a book, So that I can give my thoughts | 2.1 | Create review microservice | Tessa |  |  | x
|  | 2.2 | Create frontend design for leaving a review | Danny |  |  | x
|  | 2.3 | Create frontend functionality for leaving a review | Danny |  |  | x
|  | 2.4 | Create unit testing | Mazda |  |  | x
6 | As a seller, I want to see my list of books purchsed from me , So that I can keep track of my expenses | 6.1 | Create front-end for list of books purchased from seller | Danny |  |  | x
|  | 6.2 | Create front-end functionality for books purchased from seller | Danny |  |  | x
|  | 6.3 | Create back-end api for books purchased from seller | Tessa |  |  | x
|  | 6.4 | Create front-end and back-end testing | Clinton |  |  | x
15 | As a user, I want to be able to edit my profile, so that I can keep my details up to date | 15.1 | Create profile page | Danny |  |  | x
|  | 15.2 | Create front-end functionality for editing profile details for user. | Danny |  |  | x
|  | 15.3 | Create api for editing user profile details. | Tessa |  |  | x
|  | 15.4 | Create front-end testing for editing user details | Clinton |  |  | x

## Sprint 4
sd | SPRINT #4 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
10 | As a registered customer, I want to sell used books, So that I can give it to another person | 10.1 | Create wireframe for inventory page | Harris |  |  | x
|  | 10.2 | Create front-end for selling books page | Harris |  |  | x
|  | 10.3 | Create front-end functionality for selling books | Harris |  |  | x
|  | 10.4 | Create back-end functionality for selling used books | Tessa |  |  | x
|  | 10.5 | Create unit tests | Clinton |  |  | x
6 | As a seller, I want to see my list of books purchased from me , So that I can keep track of my expenses | 6.1 | Create front-end for list of books purchased from seller | Danny |  |  | x
|  | 6.2 | Create front-end functionality for books purchased from seller | Danny |  |  | x
|  | 6.3 | Create back-end api for books purchased from seller | Tessa |  |  | x
|  | 6.4 | Create front-end and back-end testing | Clinton |  |  | x
17 | As an admin, I want to be able to download a report of all sales in a period of time, So that I can analyse them | 17.1 | Create frontend report menu | Danny |  |  | x
|  | 17.2 | Frontend functionality | Danny |  |  | x
|  | 17.3 | Backend report API | Tessa |  |  | x
|  | 17.4 | Unit tests | Clinton |  |  | x
30 | As a customer, I want to leave a review on a seller, so that I can portray my experience | 30.1 | Create seller page front end | Harris |  |  | x
|  | 30.2 | Create seller reviews microservice | Harris |  |  | x
|  | 30.3 | Update front end to display reviews |  |  |  | x
|  | 30.4 | Test review on seller | Clinton |  |  | x
20 | As a user, I want to be able to update my password, So that I can keep my account secure | 20.1 | Create update password page for front end | Danny |  |  | x
|  | 20.2 | Update database for new password | Harris |  |  | x
|  | 20.3 | Test new password updates password | Clinton |  |  | x
27 | As a customer, I want to share a book, so that I can give other people the chance to read it | 27.1 | Create share book front end page | Harris |  |  | x
|  | 27.2 | Create share book backend functionality | Harris |  |  | x
|  | 27.3 | Test share functionality | Clinton |  |  | x
26 | As a customer, I want to contact the admin, so that I can communicate | 26.1 | Create front-end for user contacting admin | Harris |  |  | x
|  | 26.2 | Create front-end functionality for user contacting admin | Harris |  |  | x
|  | 26.3 | Create back-end functionality for user contacting admin | Harris |  |  | x
|  | 26.4 | Create tests | Clinton |  |  | x
8 | As an registered customer, I want to be able to cancel my order within 2 hours, So that I can undo the purchase | 8.1 | Create cancel order button in transactions | Danny |  |  | x
|  | 8.2 | Frontend functionality for canceling | Danny |  |  | x
|  | 8.3 | Update database on deletion | Harris |  |  | x
|  | 8.4 | Unit tests | Clinton |  |  | x
23 | As a admin, I want to moderate user reviews, so that I can maintain a clean environment | 23.1 | Create admin review list | Danny |  |  | x
|  | 23.2 | Frontend functionality | Danny |  |  | x
|  | 23.3 | Backend delete post endpoint | Tessa |  |  | x
|  | 23.4 | Unit tests | Mazda |  |  | x
24 | As a customer, I want to use paypal as a payment gateway, so that I can purchase the book | 24.1 | Link payment page with paypal services | Harris |  |  | x
25 | As a admin, I want to block a user, so that I can stop them from accessing the website | 25.1 | Create front-end for blocking a user | Danny |  |  | x
|  | 25.2 | Create front-end functionality for blocking a user | Danny |  |  | x
|  | 25.3 | Create back-end functionality for blocking a user | Harris |  |  | x
|  | 25.4 | Create tests | Clinton |  |  | x
29 | As a customer, I want to search books based on seller, so that I can narrow down my search | 29.1 | Create front-end for searching books based on seller | Harris |  |  | x
|  | 29.2 | Create front-end functionality to search books based on seller | Harris |  |  | x
|  | 29.3 | Create back end functionality for searching books based on seller | Harris |  |  | x
|  | 29.4 | Create tests | Clinton |  |  | x

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | As a user, I want to sign up, So that my information is stored | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As an admin, I want to reject new user accounts so that I can prevent them from accessing the full system | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a customer, I want to view the catalogue of books, So that I can see if a book is available | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As an admin, I want to approve new user accounts so that I can grant them more features | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As a registered user, I want to sign in, so that I can access my account | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A