## Sprint 1
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
21 | As a user, I want to sign up, So that my information is stored | 21.1 | Create wireframe for front end | Harris |  |  | X
|  | 21.2 | Create front end for sign up page | Mazda |  |  | X
|  | 21.3 | Make front end mobile responsive | Mazda | X
|  | 21.4 | Create user database | Harris |  |  | X
|  | 21.5 | Connect database with front end to insert users | Harris |  |  | X
|  | 21.6 | Test users are inserting correctly to database | Mazda | X
12 | As an admin, I want to reject new user accounts so that I can prevent them from accessing the full system | 12.1 | Create wireframe for admin page | Danny |  |  | X
|  | 12.2 | Create front end for admin page | Danny |  |  | X
|  | 12.3 | Connect database with front end | Danny |  |  | X
|  | 12.4 | Code back end for admins to reject unapproved users | Harris |  |  | X
|  | 12.5 | Test the database entry is being updated when rejected | Clinton | X
7 | As a customer, I want to view the catalogue of books, So that I can see if a book is available | 7.1 | Create wireframe for catalogue book page | Mazda |  |  | X
|  | 7.2 | Set up code for front end structure to view | Mazda |  |  | X
|  | 7.3 | Set up with back end code to view books | Mazda | X
|  | 7.4 | Test funcitonality of customer view catalogue of books | Mazda | X
4 | As an admin, I want to approve new user accounts so that I can grant them more features | 4.1 | Create wireframe for admin page | Danny |  |  | X
|  | 4.2 | Create front end for admin page | Danny |  |  | X
|  | 4.3 | Connect database with front end | Danny |  |  | X
|  | 4.4 | Code back end for admins to approve unapproved users | Harris |  |  | X
|  | 4.5 | Test the database entry is being updated when approved | Clinton |  | X
22 | As a registered user, I want to sign in, so that I can access my account | 22.1 | Create wireframe for front end | Clinton |  |  | X
|  | 22.2 | Create front end for login page | Mazda |  |  | X
|  | 22.3 | Make front end mobile responsive | Mazda | X
|  | 22.4 | Connect database with front end to access users | Tessa |  |  | X
|  | 22.5 | Test the system is retrieving the correct users | Clinton |  | X

## Sprint 2
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
3 | As a customer, I want to pay for a book, So that I can own it | 3.1 | Create mock-up for book page | Harris | X
|  | 3.2 | Create front end for book page | Harris | X
|  | 3.3 | Create dummy payment page front end | Harris | X
|  | 3.4 | Create transaction microservice | Tessa | X
|  | 3.5 | Link transaction to user table | Harris/Danny/Tessa | X
|  | 3.6 | Implement paypal option for payment | Harris/Danny/Tessa | X
|  | 3.7 | Write unit tests for tasks | Clinton/Mazda | X
10 | As a customer, I want to sell used books, So that I can get rid of the book | 10.1 | Create wireframe for inventory page | Harris | x
|  | 10.2 | Create front-end for selling books page | Haris | x
|  | 10.3 | Create front-end functionality for selling books | Harris | x
|  | 10.4 | Create back-end functionality for selling books | Harris/Danny/Tessa | x
|  | 10.5 | Create unit tests | Clinton/Mazda | x
11 | As a customer, I want to view availability of a book, So that I can purchase it | 11.1 | Create wireframe for book page | Harris | x
|  | 11.2 | Create front-end for viewing availability of books | Harris | x
|  | 11.3 | Create front-end functionality for viewing book availability | Harris | x
|  | 11.4 | Create back-end functionality for viewing book availability | Harris/Danny/Tessa | x
|  | 11.5 | Create unit tests | Clinton/Mazda | x
1 | As a customer, I want to search for books, So that I can find certain books to buy | 1.1 | Create Wireframes | Danny | x
|  | 1.2 | Create front end page design | Danny | x
|  | 1.3 | Create front end page functionality | Danny | x
|  | 1.4 | Create back end functionality | Harris/Danny/Tessa | x
|  | 1.5 | Create unit tests | Clinton/Mazda | x
5 | As a Customer, I want to see my list of transactions , So that I can keep track of my expenses | 5.1 | Create Wireframes | Danny | x
|  | 5.2 | Create front end page design | Danny | x
|  | 5.3 | Create front end page functionality | Danny | x
|  | 5.4 | Create back end functionality | Harris/Danny/Tessa | x
|  | 5.5 | Create unit tests | Clinton/Mazda | x

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | As a user, I want to sign up, So that my information is stored | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As an admin, I want to reject new user accounts so that I can prevent them from accessing the full system | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a customer, I want to view the catalogue of books, So that I can see if a book is available | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As an admin, I want to approve new user accounts so that I can grant them more features | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As a registered user, I want to sign in, so that I can access my account | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A